## Лист1
Inception
|  | Analyst | Architect | Project Manager | Test Designer
I | Use-Case | 1d
| Business Requirements |  |  | 1d |  |  |  | Use-Case | 20%
| Functional Requirements |  | 1d |  |  |  |  | Business Requirements | 100%
| Risk List |  |  | 1d |  |  |  | Functional Requirements | 100%
| Glossary | 0,5d | 0,5d |  |  |  |  | Risk List | 25%
II | Use-Case |  | 1d |  |  |  |  | Glossary | 40%
| Business Requirements | 0,5d | [5 empty] | Test Plan | 10%
| Functional Requirements | 0,5d
| Risk List | 0,5d |  | 0,5d
| Glossary | 0,5d | 0,5d |  | 0,5d
| Test Plan |  |  |  | 1d
III | Use-Case |  |  |  | 0,5d
| Business Requirements | 1d |  | 0,5d
| Functional Requirements |  |  | 0,5d
| Risk List |  |  | 0,5d
| Glossary | 0,5d | 0,5d |  | 0,5d
| Test Plan |  | 0,5d
Elaboration
|  | Software Architect | System Analyst | Designer | Implementer | Test Designer | Tester | Project Manager
I | Software Architecture Document | 5d | [5 empty] | 0.5d
| Use Case |  | 3d |  |  |  |  | 0.5d
| Design Model |  |  | 4d |  | 0.5d
| Glossary | 0.5d | 0.5d
| Analysis Model |  | 1d
II | Software Architecture Document | 2d | 1d | 1d |  | 0.5d |  | 0.5d |  | Software Architecture Document | 100%
| Use Case | 0.5d |  | 0.5d |  | 0.5d |  |  |  | Use Case | 80%
| Design Model |  | 1d | 2d |  |  |  | 0.5d |  | Design Model | 60%
| Analysis Model |  |  | 3d |  | 0.5d |  |  |  | Analysis Model | 90%
| Service Model | 0.5d |  | 2d |  | 0.5d |  |  |  | Service Model | 60%
| Test Plan |  | 0.5d |  | 0.5d | 3d | 0.5d |  |  | Test Plan | 30%
| Test Script |  |  |  | 0.5d | 6d | 1d |  |  | Test Script | 40%
| Glossary |  | 0.5d | 0.5d | 0.5d |  |  |  |  | Glossary | 80%
| Risk List |  |  |  | 0.5d |  |  | 2d |  | Risk List | 50%
| Implementation Element |  |  | 0.5d | 7d | 0.5d | 0.5d | 1d |  | Implementation Element | 40%
III | Use Case | 2d |  |  |  | 0.5d |  | 2d
| Design Model |  |  | 0.5d
| Analysis Model |  |  | 0.5d |  | 0.5d |  | 0.5d
| Service Model |  | 0.5d | 0.5d |  | 0.5d
| Test Plan |  |  |  |  | 0.5d
| Test Script |  |  |  |  | 1d | 3d
| Glossary |  |  |  |  | 0.5d |  | 1d
| Risk List | [6 empty] | 1d
| Implementation Element |  |  |  | 0.5d | 0.5d | 0.5d | 0.5d
Construction
I |  | Software Architect | System Analyst | Designer | Implementer | Test Designer | Tester | Project Manager | Technical Writer | Course Developer | Graphic Artist
| Software Architecture Document | 4d | 0.5d | 1d |  | 0.5d |  | 0.5d | 0.5d |  | 1d
| Use Case | 5d | 2d | 2d | 3d | 0.5d |  |  |  |  | 0.5d
| Glossary | 0.5d |  | 0.5d |  | 0.5d
| Design Model |  | 0.5d | 7d |  |  |  |  | 1d |  | 1d
| Service Model |  |  | 3d
| Risk List |  | 0.5d |  |  |  |  | 4d | 1d
| Training Materials |  |  |  | 1d | 1d | 1d | 1d | 2d | 3d
| Test Script |  |  |  | 0.5d | 4d | 2d |  | 1d
II | Software Architecture Document | 0.5d |  | 0.5d |  |  |  |  | 0.5d |  |  | Software Architecture Document | 100%
| Use Case | 3d | 0.5d |  | 2d | 0.5d | 2d |  | 1d |  |  | Use Case | 100%
| Glossary | 0.5d |  |  | 0.5d |  |  |  | 0.5d |  |  | Glossary | 100%
| Design Model |  |  | 0.5d |  | 0.5d |  |  |  |  | 0.5d | Design Model | 100%
| Service Model |  |  | 8d |  | 0.5d |  |  | 0.5d |  |  | Service Model | 100%
| Risk List | [9 empty] | 0.5d | Risk List | 75%
| Installation Artifacts |  |  |  | 2d |  |  | 1d | 3d | 2d | 2d | Installation Artifacts | 90%
| Implementation Element |  | 0.5d |  | 6d | 2d | 0.5d |  |  |  | 0.5d | Implementation Element | 90%
| Product Artwork | 0.5d | [6 empty] | 1d |  | 7d | Product Artwork | 100%
| User Support Material | 1d | 0.5d |  |  | 0.5d |  | 1d | 4d | 2d |  | User Support Material | 40%
| Test Script |  |  |  | 3d | 0.5d | 2d |  | 2d |  | 2d | Test Script | 80%
| Training Materials | 0.5d |  |  | 2d | 0.5d | 2d |  |  | 1d | 0.5d | Training Materials | 95%
III | Use Case | 2d |  |  | 0.5d |  | 0.5d | 0.5d | 0.5d | 0.5d
| Glossary | [7 empty] | 0.5d
Service Model
| Risk List | [6 empty] | 0.5d
| Installation Artifacts | [5 empty] | 0.5d | 0.5d | 0.5d | 0.5d | 0.5d
| Implementation Element | 0.5d |  | 0.5d | 0.5d | 0.5d | 2d | 0.5d | 2d |  | 0.5d
| Product Artwork | [6 empty] | 0.5d | 0.5d | 0.5d | 2d
| User Support Material |  | 1d | [5 empty] | 2d |  | 0.5d
| Training Materials |  |  |  | 0.5d |  |  | 0.5d | 0.5d | 0.5d
Transition
|  | Analyst | Tester | Project Manager | Test Designer | Integrator
I | Risk List | 0,5d |  | 1d
| Test Plan |  | 1d |  | 0,5d
| User Support Material |  |  |  |  | 1d
| Implementation Elements |  | 0,5d |  |  | 1d
II | Risk List | 0,5d |  | 0,5d |  |  |  | Risk List | 100%
| Test Plan |  | 0,5d |  | 0,5d |  |  | Test Plan | 100%
| User Support Material | 1d |  | 0,5d |  | 0,5d |  | User Support Material | 100%
| Implementation Elements |  | 0,5d |  |  | 0,5d |  | Implementation Elements | 100%
| Installation Verification Procedurs |  |  |  | 0,5d | 0,5d |  | Installation Verification Procedurs | 100%
| Product | 0,5d |  | 1d |  | 1d |  | Product | 100%
III | Risk List | 0,5d |  | 0,5d
| Test Plan |  | 0,5d |  | 0,5d
| User Support Material | 0,5d |  |  |  | 0,5d
| Implementation Elements |  | 0,5d |  |  | 0,5d
| Installation Verification Procedurs | 0,5d |  | 0,5d |  | 0,5d
| Product | 0,5d |  | 0,5d |  | 1d